## All Test Cases
Test Case ID | Module / Area | Test Type | Priority | Preconditions | Test Data | Test Steps | Expected Result | Actual Result / Live Observation | Status | Defect ID | Developer Fix / Recommendation | Evidence / Notes
SMK-001 | Home page | Smoke | Critical | Clean browser session | https://jeevadentalclinic.com/#smile-studio | 1. Open the URL. 2. Wait for the page to finish loading. | Page loads over HTTPS without a blocking error. | Page reached document.readyState=complete. | Pass
SMK-002 | Home page | Smoke | High | Home page loaded | None | 1. Check logo, hero heading, primary CTA, phone, WhatsApp, address. | Clinic identity and primary conversion controls are visible and readable. | Observed in live page. | Pass
SMK-003 | Navigation | Smoke | High | Home page loaded | None | 1. Click Book an Appointment. | Page scrolls to or opens the booking section. | Available as #booking link; verify scroll on each browser. | Not Run |  | Test on desktop and mobile.
SMK-004 | Navigation | Smoke | High | Home page loaded | None | 1. Click About Us, Services, Before & After, Reviews, Our Team, Contact. | Each link lands on the intended section without a blank page. | Internal targets mostly present; execute browser check. | Not Run
SMK-005 | Blog | Smoke | Medium | Internet connection | /blog | 1. Open /blog. | Blog page loads without 4xx/5xx error. | Blog page loaded; showed No articles found in fetched state. | Pass |  | Confirm empty state is intentional.
SMK-006 | Service CTA | Smoke | High | Home page loaded | Each of 10 services | 1. Click Book Now for every service. | Booking section opens and intended treatment is selected or clearly passed. | Not submitted in production. | Not Run |  | Use sandbox or test data.
SMK-007 | Service CTA | Smoke | High | Home page loaded | Each of 10 services | 1. Click Enquire for every service. | Enquiry form opens with correct treatment name. | Not submitted in production. | Not Run |  | Use sandbox or test data.
SAN-001 | Smile Studio | Sanity | High | Smile Studio visible | Patient Experience filter | 1. Click Patient Experience. | Correct cards appear or a clear intentional empty state appears. | 0 cards and no clear empty-state message. | Fail | BUG-001 | Add categorized cards, remove unused filter, or show an intentional empty state.
SAN-002 | Assets | Sanity | High | Page fully loaded | Gallery Preview and UPI QR | 1. Reload page. 2. Inspect both images visually. | Both images render with non-zero dimensions. | Both were detected with natural size 0x0. | Fail | BUG-002; BUG-003 | Repair image URLs and verify in Chrome, Safari, Android, and iOS.
SAN-003 | Payment actions | Sanity | High | Payment section visible | UPI, Pay apps, screenshot, calendar | 1. Click each action in a payment sandbox. | Each action opens the correct approved destination or performs its intended action. | Several actions have href="#". | Fail | BUG-004 | Replace placeholder anchors with tested URLs or click handlers.
SAN-004 | Confirmation copy | Sanity | Medium | Booking sandbox available | Valid synthetic patient | 1. Complete a sandbox booking. 2. Inspect confirmation. | Confirmation consistently names Jeeva Dental Clinic. | Rendered content included NEXUS Dental Care. | Fail | BUG-005 | Centralize clinic name in configuration and update confirmation copy.
UI-001 | Header responsive layout | UI | Medium | Header loaded | Desktop/mobile widths | Resize to 320, 375, 414, 768, 1024, 1280 px. | No overlap, clipping, or inaccessible menu. |  | Not Run
UI-002 | Hero section | UI | Medium | Home page loaded | Desktop/mobile widths | Inspect hero image and appointment CTA at all widths. | Image maintains aspect ratio and CTA remains visible without horizontal scroll. |  | Not Run
UI-003 | Service cards | UI | Medium | Services loaded | 10 service cards | Inspect every card. | Consistent image ratio, label, title, description, and CTA placement. |  | Not Run
UI-004 | Gallery filter buttons | UI | Medium | Smile Studio visible | All five filters | Check default, hover, focus, and selected states. | Active state is visually distinct and accessible. |  | Not Run
UI-005 | Gallery grid | UI | Medium | Smile Studio visible | All filters | Switch filters repeatedly. | No blank columns, stale cards, layout jumps, or hidden-card gaps. |  | Not Run
UI-006 | Booking steps | UI | Medium | Booking visible | Steps 1 to 4 | Inspect desktop and mobile. | Steps remain ordered and understandable. |  | Not Run
UI-007 | Date/time controls | UI | Medium | Booking visible | Today, tomorrow, available slot | Inspect selected, available, unavailable, and recommended states. | States are distinguishable by more than color. |  | Not Run
UI-008 | Form validation | UI | Medium | Booking/enquiry/review visible | Empty form | Submit empty forms. | Errors are adjacent to correct field and readable. |  | Not Run
UI-009 | Modal dialogs | UI | Medium | Modal open | Enquiry/confirmation/payment modal | Inspect close, backdrop, Escape, and focus. | Modal is clear, closable, and does not leak focus. |  | Not Run
UI-010 | Emergency floating controls | UI | Medium | Home loaded | Emergency triage widget | Scroll through page on mobile and desktop. | Floating controls do not cover form fields or CTAs. |  | Not Run
UI-011 | Payment section | UI | Medium | Payment section visible | Approved payment data | Inspect amount, UPI ID, QR, instructions, and CTA. | Information is associated, readable, and unambiguous. |  | Not Run
UI-012 | Typography/content | UI | Medium | Page loaded | All page sections | Check font loading, capitalization, and contrast. | No unexpected fallback, overflow, or inconsistent copy. |  | Not Run
UI-013 | Images | UI | Medium | Page loaded | All images | Inspect every image and alt text. | Meaningful images load and have useful alternatives. |  | Not Run
UI-014 | Footer | UI | Medium | Page loaded | Footer links | Scroll to footer. | Links, hours, phone, email, and address are readable. |  | Not Run
UI-015 | Zoom/reflow | UI | Medium | Page loaded | 200% browser zoom | Zoom to 200% and navigate. | No critical content or action becomes inaccessible. |  | Not Run
FE-001 | Hash navigation | Frontend | Medium | Page loaded | Each hash link | Refresh at #about, #services, #smile-studio, #booking, #contact. | Correct section loads and scroll position is sensible. |  | Not Run
FE-002 | Browser history | Frontend | Medium | Navigate between routes | Home and blog | Use Back and Forward. | History behavior is predictable and state is not lost unexpectedly. |  | Not Run
FE-003 | No-JavaScript fallback | Frontend | Medium | Page loaded | None | Disable JS if possible and reload. | Usable fallback or explicit limitation; no misleading empty shell. |  | Not Run
FE-004 | Slow network | Frontend | Medium | Network throttling available | Slow 3G | Throttle network and reload. | Loaders resolve and failures have useful messages. |  | Not Run
FE-005 | Offline failure | Frontend | High | Network can be disconnected | Page loaded | Disconnect network and use a form. | No false success; retry/failure state appears. |  | Not Run
FE-006 | Double submit | Frontend | High | Sandbox available | Valid sandbox data | Double-click every submit button. | Only one request or confirmation is produced. |  | Not Run
FE-007 | Form refresh | Frontend | Medium | Form is visible | Entered synthetic data | Enter data and refresh. | Data-loss behavior is intentional and safe. |  | Not Run
FE-008 | Multi-tab isolation | Frontend | Medium | Two browser tabs available | Two tabs | Use different booking selections in two tabs. | State does not leak between tabs. |  | Not Run
FE-009 | Console errors | Frontend | Medium | DevTools available | Page loaded | Navigate and inspect browser console. | No uncaught JavaScript errors or failed modules. |  | Not Run
FE-010 | Network payload | Frontend | High | Sandbox and DevTools available | Sandbox APIs | Use DevTools Network during booking/enquiry. | Correct endpoint, method, payload, status handling, and no sensitive data in URL. |  | Not Run
FE-011 | Hard reload/cache | Frontend | Medium | Browser cache enabled | Page loaded | Use hard reload and normal reload. | Assets remain available and no stale broken state appears. |  | Not Run
BK-001 | Appointment booking | Functional | High | Booking visible | Empty submission | Click Confirm Appointment Booking with no values. | Required errors appear and no request is sent. |  | Not Run
BK-002 | Appointment booking | Functional | Critical | Sandbox available | Valid booking | Enter valid name, phone, email, treatment, doctor, date, time and submit. | Correct booking/payment path and acknowledgement appear. |  | Not Run
BK-003 | Patient name | Functional | High | Booking visible | Eleanor Vance; O'Brien; Kannada text | Enter names with spaces, hyphen, apostrophe, Kannada characters. | Accepted according to business rule and displayed safely. |  | Not Run
BK-004 | Patient name | Functional | High | Booking visible | 123; <script>alert(1)</script> | Enter invalid/script values. | Rejected or encoded; no script executes. |  | Not Run
BK-005 | Phone validation | Functional | High | Booking visible | +917676476858 | Enter valid +91 number. | Accepted according to approved rule. |  | Not Run
BK-006 | Phone validation | Functional | High | Booking visible | 7676476858 | Enter valid 10-digit number. | Accepted according to approved rule. |  | Not Run
BK-007 | Phone validation | Functional | High | Booking visible | 123; abc; whitespace; 30 digits | Try invalid phone values. | Rejected with useful validation message. |  | Not Run
BK-008 | Email validation | Functional | High | Booking visible | test.patient@example.com | Enter valid email. | Accepted. |  | Not Run
BK-009 | Email validation | Functional | High | Booking visible | test@; blank; whitespace; very long | Try malformed values. | Rejected or normalized correctly. |  | Not Run
BK-010 | Consultation mode | Functional | High | Booking visible | in_clinic to online_video | Switch modes. | Fee, instructions, payment path, and confirmation change consistently. |  | Not Run
BK-011 | Consultation mode | Functional | High | Booking visible | online_video to in_clinic | Switch back. | Online-only payment instructions disappear or are disabled. |  | Not Run
BK-012 | Treatment select | Functional | High | Booking visible | All 10 treatments | Select every treatment. | Correct value and label retained downstream. |  | Not Run
BK-013 | Doctor select | Functional | High | Booking visible | Dr Jeevan; First Available | Select every doctor option. | Selected doctor is retained in request and confirmation. |  | Not Run
BK-014 | Date availability | Functional | High | Booking visible | Today, tomorrow, Sunday, Monday, custom date | Select each date type. | Past, closed, and unavailable dates are enforced. |  | Not Run
BK-015 | Date/time dependency | Functional | High | Booking visible | Change date after time selection | Select time, change date, inspect time. | Old time is cleared if not valid for new date. |  | Not Run
BK-016 | Time selection | Functional | High | Booking visible | Every available slot | Select each slot one at a time. | Exactly one slot is selected and submitted. |  | Not Run
BK-017 | Server timeout | Functional | Critical | Sandbox available | Sandbox/network throttle | Submit valid booking during timeout. | Retry guidance appears and no duplicate appointment is created. |  | Not Run
BK-018 | Server validation error | Functional | High | Sandbox available | Invalid synthetic payload | Submit invalid data to sandbox. | Field/form error appears and safe data is preserved. |  | Not Run
BK-019 | Booking confirmation | Functional | Critical | Sandbox available | Valid synthetic booking | Complete sandbox booking. | Correct clinic, ID, treatment, patient, date, and time appear. |  | Not Run
BK-020 | Refresh after booking | Functional | High | Confirmation displayed | Confirmation visible | Refresh page. | No duplicate booking is created. |  | Not Run
ENQ-001 | Treatment enquiry | Functional | Medium | Home page loaded | Open each Enquire button | Click every service Enquire button. | Correct treatment name is populated. |  | Not Run
ENQ-002 | Treatment enquiry | Functional | Medium | Enquiry modal open | Empty form | Submit empty enquiry. | Name and phone errors appear; no request sent. |  | Not Run
ENQ-003 | Treatment enquiry | Functional | Medium | Sandbox available | Valid name and phone | Submit valid enquiry. | Acknowledgement appears and one request is created. |  | Not Run
ENQ-004 | Treatment enquiry | Functional | Medium | Enquiry modal open | WhatsApp, Phone Call, Email | Select each preferred reply mode and submit in sandbox. | Selected preference is retained and used for follow-up. |  | Not Run
ENQ-005 | Treatment enquiry | Functional | Medium | Enquiry modal open | Punctuation/line breaks | Enter optional question. | Text is retained safely. |  | Not Run
ENQ-006 | Treatment enquiry | Functional | Medium | Enquiry modal open | Cancel action | Click Cancel. | Modal closes without submitting. |  | Not Run
ENQ-007 | Treatment enquiry | Functional | Medium | Valid sandbox data | Double click | Double-click submit. | One enquiry only. |  | Not Run
REV-001 | Review form | Functional | Medium | Review section visible | Empty form | Submit with no values. | Required errors appear. |  | Not Run
REV-002 | Review form | Functional | Medium | Review section visible | 1 to 5 stars | Select each rating. | Selected rating is visible and submitted correctly. |  | Not Run
REV-003 | Review form | Functional | Medium | Review section visible | All treatment tags | Select each treatment. | Correct treatment tag retained. |  | Not Run
REV-004 | Review form | Functional | Medium | Review section visible | Blank optional dentist | Leave dentist blank and submit valid review in sandbox. | Form accepts blank optional field. |  | Not Run
REV-005 | Review form | Functional | Medium | Review section visible | HTML/script in feedback | Enter markup/script. | Content is escaped/rejected; no stored XSS. |  | Not Run
REV-006 | Review form | Functional | Medium | Sandbox available | Valid synthetic review | Submit review. | Acknowledgement and moderation state are correct. |  | Not Run
EMG-001 | Emergency triage | Functional | High | Home page loaded | Open widget | Open emergency triage. | Panel opens promptly and does not obscure key CTA. |  | Not Run
EMG-002 | Emergency triage | Functional | High | Triage open | Every condition | Select every emergency condition. | Correct first-aid and warning text appears. |  | Not Run
EMG-003 | Emergency triage | Functional | High | Triage open | Change condition | Click Change Condition and choose another. | Previous state clears and new guidance replaces it. |  | Not Run
EMG-004 | Emergency triage | Functional | High | Triage open | Clinic hotline | Click Call Hotline/Call Clinic Now. | Correct approved number opens. |  | Not Run
EMG-005 | Emergency triage | Functional | High | Triage open | WhatsApp dispatch | Click WhatsApp Dispatch. | Approved WhatsApp destination and context open. |  | Not Run
EMG-006 | Emergency triage | Functional | High | Triage request open | Empty request | Submit without name/phone. | Required errors appear and no request sent. |  | Not Run
EMG-007 | Emergency triage | Functional | High | Sandbox available | Valid synthetic request | Submit valid emergency request. | Priority acknowledgement has correct patient, location, and request ID. |  | Not Run
EMG-008 | Emergency triage | Functional | High | Acknowledgement open | Close/reopen | Close and reopen triage. | No stale emergency state remains. |  | Not Run
PAY-001 | Payment | Functional | High | Sandbox pricing matrix | All consultation modes/treatments | Compare displayed amount for each combination. | Amount matches approved pricing matrix. |  | Not Run
PAY-002 | Payment | Functional | High | Approved test UPI | UPI QR | Scan on Android and iOS. | QR resolves to approved UPI destination. |  | Not Run
PAY-003 | Payment | Functional | High | Approved UPI ID | UPI copy | Click Copy. | Copied value exactly matches approved ID. |  | Not Run
PAY-004 | Payment | Functional | High | Supported mobile | GPay/PhonePe/Paytm | Click pay action. | Correct app opens or useful fallback appears. |  | Not Run
PAY-005 | Payment | Functional | High | Supported mobile | Screenshot share | Click screenshot WhatsApp action. | Approved clinic WhatsApp opens with correct context. |  | Not Run
PAY-006 | Calendar | Functional | High | Supported calendar device | Valid appointment | Click Add to Calendar. | Event contains correct date, time, timezone, clinic, address, notes. |  | Not Run
PAY-007 | Payment | Functional | High | Payment sandbox | Payment failure/cancel | Cancel or fail payment. | Appointment is not falsely confirmed. |  | Not Run
NAV-001 | External links | Functional | Medium | Home page loaded | Phone/email/maps/social | Click each contact link. | Correct destination/number/recipient opens. |  | Not Run
NAV-002 | Footer social links | Functional | Medium | Feature is available | Footer visible | Click Facebook, YouTube, Twitter, Instagram. | Links point to official clinic pages, not generic homepages. |  | Not Run
NAV-003 | Blog categories | Functional | Medium | Feature is available | Blog loaded | Click every category filter. | URL encoding, filtering, reset, and empty state are correct. |  | Not Run
A11Y-001 | Accessibility | Accessibility | Medium | Page loaded | Keyboard navigation | Tab through header, CTAs, gallery, forms. | Visible focus and logical order. |  | Not Run
A11Y-002 | Accessibility | Accessibility | Medium | Page loaded | Screen reader labels | Read all form controls. | Every input has an accessible name. |  | Not Run
A11Y-003 | Accessibility | Accessibility | Medium | Modal open | Modal focus | Open/close modal using keyboard. | Focus is trapped/returned appropriately. |  | Not Run
A11Y-004 | Accessibility | Accessibility | Medium | Feature is available | Errors | Submit empty forms | Errors are announced and associated with fields. |  | Not Run
A11Y-005 | Accessibility | Accessibility | Medium | Page loaded | 200% zoom | Zoom browser to 200%. | No content/action becomes inaccessible. |  | Not Run
SEC-001 | Security | Security | High | All text fields | XSS strings | Enter HTML/script into fields and submit in sandbox. | No script execution; output encoded. |  | Not Run
SEC-002 | Security | Security | High | Sandbox submission | Sensitive URL check | Inspect address bar and network. | Patient/medical data not placed in URL. |  | Not Run
SEC-003 | Security | Security | High | Repeated requests | Duplicate/rate limit | Submit repeatedly in sandbox. | Duplicate protection or rate limiting exists. |  | Not Run
SEC-004 | Security | Security | High | Page loaded | Storage check | Inspect cookies/localStorage/sessionStorage. | No unnecessary sensitive patient data stored client-side. |  | Not Run
PERF-001 | Performance | Performance | Medium | Desktop/mobile | Cold load | Measure cold load on agreed network. | Meets approved performance budget. |  | Not Run
PERF-002 | Performance | Performance | Medium | Page loaded | Images | Inspect image sizes and loading. | Images compressed/responsive/lazy-loaded as appropriate. |  | Not Run
PERF-003 | Performance | Performance | Medium | Smile Studio visible | Repeated filters | Switch filters repeatedly. | No memory leak, duplicate cards, or growing delay. |  | Not Run
PERF-004 | Performance | Performance | Medium | Modal controls | Repeated modals | Open/close modal repeatedly. | No overlay, scroll-lock, or focus leak. |  | Not Run

## Bugs and Fixes
Defect ID | Severity | Module | Bug Summary | Steps to Reproduce | Expected Result | Actual Result | Business/User Impact | Developer Fix | Retest Steps | Defect Status
BUG-001 | High | Smile Studio | Patient Experience filter displays zero cards | 1. Open #smile-studio. 2. Click Patient Experience. | Patient Experience cards or intentional empty state. | Filter active but 0 cards and no clear empty-state message. | Users may think gallery is broken or clinic lacks evidence. | Add correctly categorized cards; or remove filter; or add clear empty state and CTA. | Open category; inspect card count and visual state on desktop/mobile. | Open
BUG-002 | High | Payment | UPI QR image is broken | 1. Open payment instructions. 2. Inspect Scan UPI QR Code image. | QR image renders with non-zero dimensions and encodes approved UPI data. | Image natural size 0x0; resolved source was homepage URL. | Patients may be unable to pay and may lose trust. | Serve valid image asset; verify QR decode, mobile scans, HTTPS, and text fallback. | Test Android and iOS with approved sandbox/payment process. | Open
BUG-003 | Medium | Gallery | Gallery Preview image is broken | 1. Open gallery preview. 2. Inspect image. | Preview image loads correctly. | Image natural size 0x0; resolved source was homepage URL. | Broken visual content and possible modal/layout issue. | Repair source URL; validate dimensions and modal behavior. | Test all gallery categories and viewport widths. | Open
BUG-004 | High | Payment/Emergency/WhatsApp/Calendar | High-risk actions use placeholder href="#" | 1. Inspect Instant WhatsApp Enquiry, Pay via apps, screenshot share, Add to Calendar, WhatsApp Dispatch. | Each action performs its advertised behavior. | DOM audit found href="#" on these actions. | Users may be redirected to top or receive no action. | Replace placeholders with approved URLs, app intents, downloadable calendar file, or tested JS handlers; add error handling. | Add regression check rejecting placeholder # in high-risk controls. | Open
BUG-005 | Medium | Appointment confirmation | Confirmation says NEXUS Dental Care | 1. Complete booking in sandbox. 2. Read confirmation. | Confirmation names Jeeva Dental Clinic. | Rendered content says NEXUS Dental Care. | Confuses patients and reduces trust. | Centralize brand name/configuration; update copy and add content regression test. | Verify every confirmation/payment/emergency acknowledgement. | Open
BUG-006 | Medium / potentially Critical | Booking/Payment | Pricing and booking states appear inconsistent | 1. Inspect consultation modes and payment instructions. 2. Compare fees. | One authoritative pricing matrix is used consistently. | Page showed FREE in-clinic, ₹100 online video, and ₹500 payment instruction states. | Patients may pay wrong amount or misunderstand booking. | Define approved pricing matrix; bind UI and backend to it; test every mode/treatment combination. | Requires clinic/product owner confirmation. | Open
BUG-007 | Medium | Footer social links | Some social links point to generic platforms | 1. Open footer. 2. Inspect Facebook, YouTube, Twitter links. | Links point to official clinic profiles or are removed. | Observed generic facebook.com, youtube.com, twitter.com targets in DOM inventory. | Users may be sent to unrelated pages. | Replace with official profile URLs or remove unused icons. | Verify target, rel attributes, and new-tab behavior. | Needs confirmation

## Summary
Project | Jeeva Dental Clinic Website
Test URL | https://jeevadentalclinic.com/#team
Focused URL | https://jeevadentalclinic.com/#smile-studio
Test Date | 11 September 2026
Testing approach | Live non-destructive manual testing plus DOM/asset/form inspection
Production submissions | Not performed
Total test cases | 101
Passed live | 3
Failed live | 4
Not run / requires sandbox | 94
Open defects | 7
Release recommendation | Do not release unrestricted conversion traffic until high-severity issues are fixed or accepted.
Important limitation | Backend delivery, payment, SMS, email, WhatsApp, calendar, and clinic scheduling require approved sandbox/test data.
Requested testing types covered | 16 of 16
Coverage details | See the Testing Types Coverage sheet for execution scope and traceability.

## Regression Suite
Regression ID | Regression Area | Steps | Expected Result | Run Status | Defect ID | Notes
REG-001 | Home load | Open site in clean session. | HTTPS page loads with title and no blocking error. | Not Run
REG-002 | Primary navigation | Click all header links and CTAs. | Correct section/route opens. | Not Run
REG-003 | Smile Studio | Run all five gallery filters. | Correct cards/empty state and active state. | Fail | BUG-001 | Patient Experience currently empty.
REG-004 | Assets | Inspect all meaningful images. | All images load with correct dimensions. | Fail | BUG-002; BUG-003 | Two broken images observed.
REG-005 | Booking validation | Submit empty booking. | Required errors appear; no request. | Pass |  | Native validation observed.
REG-006 | Booking sandbox | Complete one valid booking. | Correct confirmation values and clinic name. | Not Run | BUG-005 | Requires sandbox.
REG-007 | Enquiry/review | Run empty and valid sandbox tests. | Validation and acknowledgements correct. | Not Run
REG-008 | Emergency | Open, change condition, call, dispatch, close. | All destinations and states work. | Not Run | BUG-004 | Placeholder action exists.
REG-009 | Payment | Test QR, UPI copy, app, screenshot, calendar. | All actions work with approved sandbox data. | Not Run | BUG-002; BUG-004 | Requires test payment flow.
REG-010 | Accessibility | Keyboard, focus, labels, zoom. | Supported accessibility checks pass. | Not Run
REG-011 | Responsive | Repeat smoke on mobile and desktop. | No layout or interaction regression. | Not Run
REG-012 | Console/network | Inspect console and requests during flows. | No uncaught errors or incorrect payloads. | Not Run

## How to Use
Purpose | Copy-ready manual testing workbook for Jeeva Dental Clinic.
All Test Cases | Use this as the primary execution sheet. Fill Actual Result, Status, Defect ID, and Evidence/Notes.
Bugs and Fixes | Share this sheet with developers. After a fix, fill Defect Status and use Retest Steps.
Regression Suite | Run after every code, content, payment, backend, or hosting change.
Test data warning | Use synthetic data in staging/sandbox. Do not enter real patient or payment information without authorization.
Status values | Not Run, Pass, Fail, Blocked, Retest Required, Fixed, Needs Confirmation.
Live findings | Rows marked Fail are based on the live non-destructive checks completed on 11 September 2026.
Copying | Each row is independent. You can copy any row directly into Jira, TestRail, Excel, or a test-management tool.

## Testing Types Coverage
Requested Testing Type | Included in Workbook | Covered Test Case IDs / Areas | What to Execute | Expected Outcome | Primary Sheet
UI testing | Yes | UI-001 to UI-015; Smile Studio; booking; payment; emergency widgets | Verify layout, spacing, typography, colors, images, controls, states, modals, and visual consistency at supported sizes. | No clipping, overlap, broken images, unreadable content, or inconsistent interaction states. | All Test Cases
Frontend testing | Yes | FE-001 to FE-011 | Verify browser-side navigation, hash routes, state changes, validation, console behavior, network errors, caching, and duplicate submission protection. | Client-side behavior is stable, truthful, and free from uncaught errors. | All Test Cases
Functional testing | Yes | SMK-001 to SMK-007; BK-001 to BK-020; ENQ; REV; EMG; PAY; NAV | Execute each workflow with positive, negative, boundary, cancellation, retry, and failure scenarios. | Each feature performs its documented business function correctly. | All Test Cases
Smoke testing | Yes | SMK-001 to SMK-007 | Run the critical-path checks after deployment or build creation. | The application is usable enough for deeper testing. | All Test Cases
Sanity testing | Yes | SAN-001 to SAN-004 | After a targeted fix, retest only the changed area and its immediate dependencies. | The fix works and has not caused an obvious local regression. | All Test Cases
Regression testing | Yes | REG-001 to REG-012 | Run after code, content, payment, API, hosting, or configuration changes. | Previously working critical workflows continue to work. | Regression Suite
Appointment booking testing | Yes | BK-001 to BK-020 | Test modes, treatments, doctors, dates, slots, patient data, validation, duplicate clicks, failures, payment, and confirmation. | Only valid appointments are created with correct details and pricing. | All Test Cases
Treatment enquiry testing | Yes | ENQ-001 to ENQ-007 | Test every service enquiry, empty/valid input, reply preference, optional question, cancel, duplicate submit, and network failure. | Correct treatment and patient enquiry are captured once and acknowledged correctly. | All Test Cases
Review form testing | Yes | REV-001 to REV-006 | Test required fields, ratings, treatment tags, optional dentist, long text, special characters, XSS strings, moderation acknowledgement, and duplicates. | Review data is validated, safely stored, and correctly acknowledged. | All Test Cases
Emergency triage testing | Yes | EMG-001 to EMG-008 | Test condition selection, first-aid content, warnings, hotline, WhatsApp dispatch, required fields, request acknowledgement, close/reopen, and hours messaging. | Emergency information and contact actions are accurate, safe, and reliable. | All Test Cases
Payment and calendar testing | Yes | PAY-001 to PAY-007; BUG-002; BUG-004 | Use an approved sandbox to test pricing, QR, UPI copy, payment-app actions, screenshot sharing, calendar event, cancellation, timeout, and webhook delay. | Amounts, destinations, appointment states, and calendar details are correct; no false confirmation. | All Test Cases
Navigation and external-link testing | Yes | SMK-003 to SMK-005; NAV-001 to NAV-003 | Test hash navigation, blog route, phone, email, Maps, WhatsApp, Instagram, and footer social links. | Every link opens the correct destination and no generic or placeholder link remains. | All Test Cases
Accessibility testing | Yes | A11Y-001 to A11Y-005; UI-015 | Test keyboard access, visible focus, screen-reader labels, modal focus, error announcements, heading structure, contrast, reduced motion, and zoom/reflow. | The site remains operable and understandable for users with accessibility needs. | All Test Cases
Responsive and compatibility testing | Yes | UI-001 to UI-015; REG-011 | Repeat smoke and high-risk workflows on desktop, tablet, iOS Safari, Android Chrome, Firefox, Edge, Safari, touch, keyboard, and multiple viewport sizes. | No browser- or viewport-specific layout or functional failures. | All Test Cases / Regression Suite
Security and privacy-oriented testing | Yes | BK-004; REV-005; SEC-001 to SEC-004 | Test XSS strings, long input, HTTPS, sensitive data in URLs, duplicate/rate limits, storage, external links, and network payloads in an approved environment. | Inputs are safely handled and personal/medical data is not unnecessarily exposed. | All Test Cases
Performance and resilience testing | Yes | FE-004; FE-005; PERF-001 to PERF-004 | Test cold load, image weight, Slow 3G, offline behavior, repeated filters, repeated modal use, and service/API outage handling. | The page remains responsive and gives truthful, recoverable feedback under stress. | All Test Cases